## Product Backlog
Product Name | Product Description | Priority (Numeric) | Original Estimate (Hours) | Milestone
Establish Art Style | Choosing an art style for the game to be drawn in | 1 | 4 | Planning
Hero Walking and Running Spritesheets | Spritesheet for full walking animation or running animaiton for testing animation | 1 | 6 | Prototype
Character Concepts | Concept art for Hero, and NPCs | 1 | 5 | Planning
Control Scheme Inputs | Getting basic controls done. Walking tap, jumping tap, teleporting swipe | 1 | 7 | Prototype
Hero Jumping and Teleporting Spritesheets | Spritesheet for begin and end jump, begin and end teleport | 1 | 7 | Alpha
Hero Class: Basic Movement | Hero can move in all planned directions | 1 | 6 | Alpha
Hero Class: Teleportation | Adding the code for the teleportation in the hero class | 2 | 7 | Alpha
Basic Hero Movement | Moving the hero with the spritesheet animating | 2 | 5 | Alpha
First Enemy Spritesheet | Simple spritesheets for the first enemy | 2 | 6 | Alpha
Camera Code | Coding the camera to follow the user wherever he goes without going out of view of the background | 2 | 6 | Alpha
Teleportation Collision | Coding the teleportation to allow user to go through certain objects and collide with others | 2 | 8 | Prototype
Hero Class: Animations | Programming the animations to play correctly in the hero class | 2 | 3 | Alpha
Create Hero Class | Creating a hero class that can be used to create an instance when moving into a room | 2 | 9 | Alpha
Create Character/Enemy Class | Creating a character class and then an enemy class that can be used to programmatically create an instance of within a room | 2 | 9 | Alpha
Hero Standing Spritesheet | Simple idle animation | 3 | 3 | Alpha
Create Room Classes | Creating a base room class that specific room classes can be implement | 3 | 4 | Alpha
Environment Concepts | Concept art for each Room | 3 | 5 | Planning
Box2D Research | Learn how to use Box2D for collision and sensors | 3 | 7 | Planning
Drawing Foreground Objects | Drawing basic objects to be used for ground collision | 3 | 7 | Alpha
Cocos2Dx Research | Learn how to use Cocos2D-X | 3 | 11 | Planning
Character Sound Effects | Sound effects for character movement, jumping, attack, teleportation, interactions, etc | 4 | 2 | Alpha
Shield Enemy Spritesheets | Spritesheet for an enemy that can block the character's teleportation | 4 | 4 | Alpha
Fine tuning hero movement | Adding accelration and advanced features | 4 | 6 | Alpha
Basic Enemy AI | Able to detect the hero and pursue | 4 | 13 | Beta
Functional First Room | A working room with hero, enemy, and enviromental interactions. Camera should also be following the hero | 5 | 12 | Alpha
Level Music | Generic looping music for the level | 6 | 3 | Alpha
Environment Sound Effects | Sound effects for the enviroment, and for collision with objects. | 6 | 4 | Alpha
Foreground Objects | Foreground drawings for collision with the characters | 6 | 10 | Alpha
Hero Class: Advanced Movement | Hero can stick to walls, slide with velocity | 7 | 2 | Alpha
Parallax Backgrounds | Far, middle, and front backgrounds for each Room drawn | 7 | 4 | Beta
Teleportation Effect Tweaking | Experimenting and deciding on the teleportation effect | 7 | 5 | Beta
Ground Based Powerups | Powerups lying on the ground that can be collected | 7 | 5 | Alpha
Background Art | Draw art for first level background | 7 | 10 | Beta
Hero Class: Gameplay Elements | Adding a powerup status, and other gameplay bits | 8 | 3 | Alpha
Music Code | Coding the music into the game | 8 | 3 | Alpha
Hero Between Animation Transitions | Adding small animations that play between motion states | 8 | 4 | Alpha
Combat Music | Music for when the hero encounters enemies | 8 | 4 | Alpha
Tutorial Level | Teach user how to play the game within roughly 5 rooms | 8 | 9 | Beta
Practice Dummy Spritesheets | One nonmobile practice dummy for the tutorial level | 9 | 2 | Beta
Design First Boss | Establiush gameplay and art elements fo the first boss | 9 | 4 | Beta
First Boss Spritesheet | Develop art for the first boss | 9 | 6 | Beta
Wire Movement | Program a wire area that the character can move through | 9 | 6 | Beta
Create Level Class | Creating a level class that contains an array of rooms and controls the transitions between rooms | 9 | 7 | Beta
Advanced Enemy Spritesheets | Movement and attacking spritesheet for each advance enemy. Bosses | 9 | 11 | Beta
Debug | Debug the code | 9 | 26 | Release
Menu Design | Concept of the Menu and art for background and buttons | 10 | 3 | Beta
Pause Screen | Pause screen background | 10 | 3 | Beta
Menu and Pause Code | Coding the pause and menu screens | 10 | 3 | Beta
299

## Sprint Log
To Do |  | In Progress |  | Done
Story Name | Save points
Story Description |  | [Dylan] |  | Story Name | Room 2 lvl 1 Art outlines
User dies and respawns at a point that is not at the beginning |  |  |  | Story Description
|  | Story Name | Room 2 collision and enemy placement | User enters the fifth room of the first level
Story Estimate | 8 hour | Story Description |  | Story Estimate | 2 hour
Time of execution |  | User enters the second room and encounters enemies |  | Time of execution | 3 hours
|  | Story Estimate | 2 hour
Story Name | Main menu volume control | Time of execution |  | Story Name | Shield Guard Spritesheet
Story Description |  |  |  | Story Description
User clicks on the settings page and drags a slider to lower sound |  |  |  | Walking/defending animations for the shield guard, modified
from the original guard sprite sheet
Story Estimate | 9 hours |  |  | Story Estimate | 4 hours
Time of execution |  | [Matt] |  | Time of execution
Story Name | Save points
Story Description |  |  |  | Story Name | Room2 lvl 1 Art Complete
User dies and respawns at a point that is not at the beginning |  |  |  | Story Description
User enters the sixth room of the first level, now with colour!
Story Estimate | 8 hour |  |  | Story Estimate | 2 hour
Time of execution |  |  |  | Time of execution | 2 hours
Story Name | Design divided smaller rooms |  |  | Story Name | Main menu art
Story Description |  |  |  | Story Description
User can go to multiple small rooms in a level |  |  |  | User starts the game and sees thematic art for the main menu
|  |  |  | Story Estimate | 3 hour
Story Estimate | 1 hour |  |  | Time of execution
Time of execution |  | [Reza]
|  | Story Name | Enemy movement | Story Name | Gun guard sprite sheet
|  | Story Description |  | Story Description
User enters a room, and all enemies are moving, and attack
|  | the user when seen |  | Walking/defending animations for the gun guard, modified
|  | Story Estimate | 2 hour | from the original guard sprite sheet
|  | Time of execution |  | Story Estimate | 4 hours
|  |  |  | Time of execution | 2 hours
|  |  |  | Story Name | Room 3 lvl 1 Art outlines
Story Description
Outlines of the artwork for the game's environment in the
3rd room of the first level
|  |  |  | Story Estimate | 2 hours
Time of execution
|  |  |  | Story Name | Room 4 lvl 1 Art outlines
|  | [Stephanie] |  | Story Description
User enters the fourth room of the first level
|  |  |  | Story Estimate | 2 hour
Time of execution
|  |  |  | Story Name | Teleport collision fixes
Story Description
User can't teleport outside of the level and kill enemies magically
|  |  |  | Story Estimate | 5 hour
|  |  |  | Time of execution | 5 hour
Story Name | Room 4 collision and enemy placement
Story Description |  |  |  | Story Name | Tutorial level art outlines
User enters the fourth room and encounters enemies |  |  |  | Story Description
Story Estimate | 2 hour |  |  | User enters the tutorial level
Time of execution |  |  |  | Story Estimate | 1 hour
|  |  |  | Time of execution | 30 mins
Story Name | Room 5 collision and enemy placement
Story Description
User enters the fifth room and encounters enemies |  |  |  | Story Name | Tutorial Level
Story Estimate | 2 hour |  |  | Story Description
Time of execution |  |  |  | User enters the tutorial level, now with colour!
|  |  |  | Story Estimate | 2 hour
|  |  |  | Time of execution | 1 hour
|  |  |  | Story Name | End Room Art Outlines
Story Description
User escapes in to an empty field.
|  |  |  | Story Estimate | 1 hour
Story Name | Room 3 collision and enemy placement |  |  | Time of execution | 45 minutes
Story Description
User enters the third room and encounters enemies |  |  |  | Story Name | Hero death animation
Story Estimate | 2 hour |  |  | Story Description
Time of execution |  |  |  | User dies and the hero plays out an animation
|  |  |  | Story Estimate | 4 hour
Time of execution
|  |  |  | Story Name | Intro Story
Story Description
User sees intro text explaining the game's background story
|  |  |  | Story Estimate | 1 hour
Time of execution
|  |  |  | Story Name | End Story
Story Description
User sees end text telling them that they have beat the game!
|  |  |  | Story Estimate | 1 hour
Time of execution
|  |  |  | Story Name | Trap Box
Story Description
A box used to cover over hazards that if the hero touches he
will die
|  |  |  | Story Estimate | 2 hour
Time of execution
|  |  |  | Story Name | Level 1 backround music
Story Description
User hears ambient music across all of the rooms of the first level
|  |  |  | Story Estimate | 3 hour
Time of execution
|  |  |  | Story Name | Boxes/Extra Environment Pieces
Story Description
User sees boxes and other objects, some they can interact with
|  |  |  | Story Estimate | 4 hour
Time of execution
|  |  |  | Story Name | Room 4 lvl 1 Art Complete
Story Description
User enters the fourth room of the first level, now with colour¦!
|  |  |  | Story Estimate | 2 hour
Time of execution
|  |  |  | Story Name | Room 5 lvl 1 Art outlines
Story Description
User enters the fifth room of the first level
|  |  |  | Story Estimate | 2 hour
Time of execution
|  |  |  | Story Name | Room 5 lvl 1 Art Complete
Story Description
User enters the fifth room of the first level, now with colour!
|  |  |  | Story Estimate | 2 hour
Time of execution
|  |  |  | Story Name | Boss design
Story Description
User has to defeat the boss using TECHNIQUES
|  |  |  | Story Estimate | 2 hour
Time of execution

## Story Template
Story Name | Sample Story
Story Description
The user is able to do A and B after doing C
Story Estimate | 4 hours
Time of execution
Story Name | Hero Running SpriteSheet
Story Description
When the user makes the hero run, they will see an animation that is
going through a spritesheet of the hero running
Story Estimate | 3 hours
Time of execution
Story Name | Hero Walking SpriteSheet
Story Description
When the user makes the hero walk, they will see an animation that
is going through a spritesheet of the hero Walking
Story Estimate | 3 hours
Time of execution

## Instructions
Requirements
Update (on SVN) the Sprint Log
At the beginning of an Iteration (After Scrum Planning meeting)
At the end of an Iteration (After Scrum Review Meeting)
As often as you can in between iterations
Update Product Backlog
At the beginning of an Iteration (After Scrum Planning meeting)